## Sheet1
Planning template
Started | Completed
Before the Meet
2017-10-16 | 2017-10-16 | Update schedule statistics from previous year.
2017-10-16 | 2017-10-31 | Produce a schedule of events and estimate the duration of the sessions
2017-02-21 | 2017-04-13 | Book the pool, the equipment required and a room for the officials (for food, briefing, etc.)
2017-04-04 | 2017-04-04 | Recruit operators for the AOE and the meet management computer (these are key people and should be found early in the process)
2017-10-31 | 2017-10-31 | Predict costs, pool, expenses, etc.
2017-10-31 | 2017-10-31 | Estimate the entry fees based on the costs and the likely number of swimmers
2017-10-31 | 2017-10-31 | Decide how entry fees are to be collected (e.g. PayPal)
2017-10-17 | 2017-10-17 | If a swim shop is to be provided contact the supplier
2017-11-02 | 2017-11-02 | Produce the entry pack to include the schedule of events, the estimated timing, warm up arrangements, the conditions, venue address, plus any notes to competitors needed
2017-11-02 | 2017-10-04 | Create the meet in a meet management application (e.g. Sportsystems, Hytek, etc.)
2017-11-02 | 2017-11-02 | Send information to the entry application provider
2017-10-03 | 2017-10-03 | Obtain links to the on-line entry application and include in the entry pack
2017-10-02 | 2017-10-02 | Finalise the entry pack
2017-10-06 | 2017-10-08 | Contact hotels re: accommodation package
2017-11-09 | 2017-11-09 | Send the entry instructions and the accommodation package to last year's entrants
2017-11-10 | 2017-11-13 | Advertise the meet in the British Swimming Masters calendar, on the regional web site and any other appropriate web sites
2017-10-20 | 2017-10-20 | Estimate the number of medals and order
2017-11-09 | 2018-01-08 | Monitor the entries as they come in and deal with any queries that arise (this can be a frustrating job)
2017-11-09 | 2018-01-08 | Monitor the duration of the sessions using the promotors application provided by the entry application supplier
2017-12-01 | 2018-01-08 | Ensure that the sessions do not overrun and if all the allocated time is used close some or all of the events in the session as necessary
2017-11-15 | 2018-01-08 | Send out a request for officials (obtaining officials for a Masters meet can be the most challenging part so needs a lot of attention)
2017-11-15 | 2018-01-15 | Recruit helpers, people to help with the front desk, the medal table, taking round officials drinks and sweets
2018-01-15 | 2018-01-17 | When sufficient officials have been recruited select the referees by mutual agreement
2018-01-17 | 2018-01-17 | Send the list of officials to the referees so that they can allocate the other roles
2018-11-09 | 2018-01-09 | Contact the catering supplier, get menus (if providing a meal), select meals and drinks and order
2018-01-10 | 2018-01-15 | When entries are closed produce the event programme
2018-01-10 | 2018-01-15 | Send the meet management files to the person who will operate the meet management computer
2018-01-15 | 2018-01-15 | Estimate the number of copies of the programme and send to the printers
2018-01-15 | 2018-01-15 | Write to the pool with a list of requirements, tables and chairs and where they should be positioned
2018-01-17 | 2018-01-17 | Produce the latest British, European, World and Meet records to take to the pool
2018-01-05 | 2018-01-05 | Receive the medals from the supplier
2018-01-19 | 2018-01-19 | List all the items to be taken to the pool on the day and assemble them
2018-01-14 | 2018-01-14 | If using phone registration check all working properly
2018-01-18 | 2018-01-18 | Collect the programmes from the printers
2017-12-05 | 2018-01-23 | Purchase water, sweets, drinks, chocolates, wine etc. for the officials as appropriate
2018-01-10 | 2018-01-14 | Write to all the entrants giving any instructions needed and confirming warm-up arrangements, etc.
2018-01-16 | 2018-01-16 | Write to officials saying who the referees are and where and when to assemble, include a tailored expense claim for their use
2018-01-14 | 2018-01-14 | Write to the relay team managers to send them a Team Declaration Form, tell them when and where to hand them in
2018-01-18 | 2018-01-18 | Prepare a copy of all the entries on a memory stick
On the day of the Meet:
2018-01-19 | 2018-01-19 | Assemble all the items to take to the meet and transport to the pool
2018-01-20 | 2018-01-20 | Set up the equipment - Laptops, Printers, Tables, Chairs
2018-01-20 | 2018-01-21 | Produce and display Registration Sheets
2018-01-20 | 2018-01-20 | Display signage as appropriate
2018-01-20 | 2018-01-20 | PA – Test the PA system
2018-01-20 | 2018-01-20 | Test the timing system and scoreboard
2018-01-20 | 2018-01-21 | Produce and post the Heat Sheets
2018-01-20 | 2018-01-20 | Check the catering arrangements are as ordered
2018-01-20 | 2018-01-21 | As the meet progresses post the results and distribute the medals
2018-01-20 | 2018-01-21 | Make sure that all those claiming have expense forms and collect all completed forms (encourage forms to be completed and handed in before claimants leave)
2018-01-21 | 2018-01-21 | Collect any medals over
2018-01-21 | 2018-01-21 | Remove all paper from pool walls (heat sheets and results)
2018-01-21 | 2018-01-21 | Check all is tidy and nothing left
After the Meet
2018-01-22 | 2018-01-22 | Produce results and post on the web
2018-01-22 | 2018-01-22 | Send files to Rankings and Decathlon
2018-01-22 | 2018-01-23 | Check and send any record application to Swim England
2018-01-22 | 2018-01-25 | Check and sign all expense claims
Update Records Ledger if needed
Write “Thank you” email to all involved.
| 2018-02-11 | Update “Meet Best Performance” list and send to SSE web master for posting