| Timeline | Area to plan/organise | Managed by | Tick when complete |
| --- | --- | --- | --- |
| 4 months | Identify need for Aquasplash Festival. |  |  |
|  | Highlight events/key calendar dates Aquasplash can link to. |  |  |
|  | Identify and agree key roles and responsibilities (including young leaders). |  |  |
|  | Agree budget and financing. |  |  |
|  | Coordinate Young Aquatic Leaders Certificate (YALC). |  |  |
|  | Invite local club/sports development group involvement. |  |  |
|  | Provisional booking of facility and lifeguard cover. |  |  |
|  | Inform pupils and receive any necessary permissions from parents/carers. |  |  |
| 3 months | Confirm facility booking and lifeguard cover. |  |  |
|  | Book transport. |  |  |
|  | Plan CPD/briefing sessions for participating teaching staff. |  |  |
|  | Newsletter/invitation for parents/carers. |  |  |
|  | Check in with participating clubs/development groups. |  |  |
|  | Taster swimming sessions for pupils. |  |  |
| 2 months | Deliver CPD/briefing sessions for participating teaching staff and young leaders. |  |  |
|  | Deliver YALC theory session. |  |  |
|  | Carry out risk assessments (RAs) and DBS check as appropriate. |  |  |
|  | Newsletter/invitation reminder for parents/carers. |  |  |
|  | Check in with participating clubs/development groups. |  |  |
|  | Taster swimming sessions for pupils. |  |  |

| Timeline | Area to plan/organise | Managed by | Tick when complete |
| --- | --- | --- | --- |
| 1 month | Check in with facility. |  |  |
|  | Check in with transport provider. |  |  |
|  | Organise refreshments, prizes, awards. |  |  |
|  | Agree de-brief process for teachers and young leaders. |  |  |
|  | Agree scoring system and prepare scorecards. |  |  |
|  | Newsletter/invitation reminder for parents/carers. |  |  |
|  | Check in with participating clubs/development groups. |  |  |
|  | Taster swimming sessions for pupils. |  |  |
| 1 week – 3 days | Ensure all health and safety procedures are in place at venue. |  |  |
|  | Organise staff member to meet and greet parents/carers/supporters. |  |  |
|  | Prepare scorecards. |  |  |
|  | ‘On the Day’ brief for pupils. |  |  |
|  | Check in with participating clubs/development groups. |  |  |
|  | Check in with parents/carers. |  |  |
| Festival Day | Debrief for pupils and helpers. |  |  |
|  | Festival time! |  |  |
|  | Prize giving and networking opportunities with clubs. |  |  |
|  | Clear equipment. |  |  |
|  | Feedback from pupils and supporters. |  |  |